SOYABEAN; GESSiP PROTOCOL FOR THE ESTABLISHMENT OF MOTHER DEMONSTRATION ON

GOOD AGRICULTURAL PRACTICES (GAPs) IN SOYABEAN   PRODUCTION

VARIETY: JENGUMA MATURITY: 110-115 DAYS:  (Or AFAYAK)

YIELD: 2.5 Mt/Ha

- Select a good site-Loamy soil and well drained

- Procure improved seed from recognized seed dealers.

- Perform a germination test -85% and above means seed is good

- Prepare a good seed bed – plough/harrow and ridge across the slope

- Apply 1 bag TSP/SSP or 1.5 bags NPK per acre before ridging to bury it.

- Plant when there is adequate soil moisture

- Inoculate seed before planting with recommended inoculants: 5gm per 1kg seed

- Plant 3 seeds per hill; Plant at a spacing of 75cm by 10cm

- Weed when soybean is 10 to 14 days.

- Weed the second time when soybean is 5 weeks

- Spray with a recommended pesticide at 8 weeks (pre-flowering) (Organize a field Day 1)

- Repeat spraying at 10 weeks(flowering) and at 12 weeks (podding).

12	Regularly inspect farm for any signs of infestation or destruction by pests and diseases

- Harvest when leaves are being shed and the pods are dry (Organize a field Day 2)

- Thresh, winnow and store in clean and disinfected warehouse.

ACTION PLANS FOR FIELD DAYS: SOYABEAN

Field Day 1:

| When | Spray with a recommended pesticide at 8 weeks (pre-flowering) |
| --- | --- |
| Learning objectives – why? | - Knowing stage at which to spray - Know how to measure and mix correct quantities of insecticides - Know how to spray recommended insecticides |
| How to be organized | - At demo site - Community-wide farmers invited - Field staff and collaborators - 1 hour of observations, questions and answers, and discussions - Pictures and data for documentation and M&E schedule |
| Follow-up activities | - Visiting Baby demo sites to observe conformity |
| Materials needed | - Knapsack sprayers, insecticides, clean water, protective clothing |

Field Day 2:

| When | - Harvest when leaves are being shed and the pods are dry |
| --- | --- |
| Learning objectives – why? | - know the harvest maturity signs for soyabeans - assessing crop yield qualities |
| How to be organized | - At demo site - Community-wide farmers invited - Field staff and collaborators - 1 hour of observations, questions and answers, and discussions - Pictures and data for documentation and M&E schedule |
| Follow-up activities | - Visiting Baby demo sites to observe conformity |
| What materials needed | - Sacks for storage |